## Sheet1
Sr.No | Name | Status | Remark
1 | VPC | Completed | Make CIDR configurable
2 | Subnets | Completed
3 | Route table | Completed
4 | Security Group | Completed | RDS and EKS - provisioned
Subnet group for RDS
5 | DB parameter group | Completed | Default will be taken by RDS
6 | NACL | Completed | VPC will take care
7 | IGW | Completed | VPC will take care
8 | VPC endpoint services | In Progress
9 | NAT Gateway | Completed | VPC will take care
10 | Security Components | Need Discussion
11 | Route53 - Hosted Zone | Completed
12 | CloudFront | Completed
13 | S3 Bucket | Completed | Create IAM user with secret key and access key and attach restricted access policy
14 | EKS Cluster Provisioning | Completed
15 | Elastic Cache - Redis provisioning
16 | Opensearch - Elastic Search
17 | MSK
18 | ALB - Public | Trough HELM chart
19 | NLB - Private
20 | API Gateway | TO DO
21 | RDS - Aurora Postgres | TO DO | 1. Attach RDS security group 2.RDS subnet group 3. Dbparameter Group (Default) 4.Enable KMS key 5. Enable Performance Insights | Instance configuration Instance type Serverless v2 Minimum capacity 2 ACUs (4 GiB) Maximum capacity 2 ACUs (4 GiB)
22 | IAM Roles - for EKS cluster
23 | IAM Roles - for API gateway